## Slide 1
Test
Executive Monthly Portfolio Review
June 09, 2026 — July 09, 2026
Total Projects Analyzed: 2

## Slide 2
Portfolio Health Overview
Across the two‑project portfolio, budget performance is uniformly strong (CPI = 1.0, 0% burn), but schedule health is pressured by overdue tasks in both projects and blocker remediation is uneven, with one project carrying a large unresolved blocker backlog.
TOTAL PROJECTS
2
HEALTHY
0%
AT RISK
0%
Chart: 
| Green | Amber | Red
Projects | 0 | 2 | 0

## Slide 3
Average Project Scores across Portfolio
Chart: 
| Schedule | Budget | Milestones | Blockers | Sentiment
Average Score | 90.9 | 100 | 90.9 | 0 | 21.45

## Slide 4
Cross-Project Macro Trends
Trend Description | Direction | Severity | Affected Projects
Overdue tasks exceed 5% of total work in both projects (11.5% in Project Plan B, 6.7% in S2P), keeping schedule scores just above 85 but showing no improvement. | STABLE | MEDIUM | Project Plan B (1), S2P Project (4)
Budget scores remain at 100 with CPI = 1.0 and zero burn rate across the portfolio, indicating consistent cost control. | STABLE | LOW | Project Plan B (1), S2P Project (4)

## Slide 5
RAG Status Shifts (Period-over-Period)
No projects shifted RAG status during this period.

## Slide 6
Top Emerging Risks & Blockers
Risk Description | Urgency | Affected Projects
High volume of unresolved blockers in Project Plan B (234 of 383 items, 61% unresolved) threatens schedule and quality. | HIGH | Project Plan B (1)
Neutral‑to‑negative stakeholder sentiment in S2P Project (42.9 score, 3 negative vs 4 neutral entries) may signal growing dissatisfaction. | MEDIUM | S2P Project (4)

## Slide 7
Notable Wins & Positive Signals
Win / Positive Signal | Associated Projects
Both projects are under budget with CPI = 1.0 and no budget burn to date. | Project Plan B (1), S2P Project (4)
Schedule scores remain high (88.5 and 93.3) despite some overdue tasks. | Project Plan B (1), S2P Project (4)

## Slide 8
Strategic Recommendations
• Prioritize resolution of medium‑severity blockers in Project Plan B to reduce the 61% unresolved rate.
• Implement a focused overdue‑task reduction sprint across both projects to bring overdue percentages below 5%.
• Capture stakeholder sentiment for Project Plan B (add comments field) to enable portfolio‑wide sentiment monitoring.
• Begin tracking actual cost and burn rate to move budget signals from zero‑consumption to active monitoring.
• Set up a weekly cross‑project health review to watch schedule overdue trends and blocker clearance rates.

## Slide 9
Appendix: Detailed Portfolio Metrics
Project Name | RAG | Overall | Schedule | Budget | Blocker | Sentiment
20260708 144914 Project P | AMBER | 76 | 88 | 100 | 0 | 0
20260708 151623 S2P Proje | AMBER | 73 | 93 | 100 | 0 | 43