## Slide 1
Project Portfolio
Executive Monthly Portfolio Review
June 09, 2026 — July 09, 2026
Total Projects Analyzed: 2

## Slide 2
Portfolio Health Overview
The portfolio remains in amber overall, with strong budget performance but emerging schedule and blocker concerns. While both projects maintain a CPI of 1.0, overdue tasks are present in every project and unresolved blockers are heavily concentrated in Project Plan B, contributing to a modest decline in weighted scores.
TOTAL PROJECTS
2
HEALTHY
0%
AT RISK
0%
Chart: 
| Green | Amber | Red
Projects | 0 | 2 | 0

## Slide 3
Average Project Scores across Portfolio
Chart: 
| Schedule | Budget | Milestones | Blockers | Sentiment
Average Score | 90.9 | 100 | 90.9 | 0 | 21.45

## Slide 4
Cross-Project Macro Trends
Trend Description | Direction | Severity | Affected Projects
Overdue tasks appear in all projects (44/383 and 33/492), averaging 8.8% of total tasks overdue. | STABLE | MEDIUM | Project Plan B, S2P Project
Budget health is uniformly strong with CPI = 1.0 and 0% burn across the portfolio. | STABLE | LOW | Project Plan B, S2P Project
Weighted score is declining in S2P Project (‑2.7 points) while stable in Project Plan B, resulting in a net portfolio score drop of ~1.5 points. | DECLINING | MEDIUM | S2P Project
Unresolved blocker count is highly imbalanced: 234 in Project Plan B versus 1 in S2P Project. | STABLE | HIGH | Project Plan B

## Slide 5
RAG Status Shifts (Period-over-Period)
No projects shifted RAG status during this period.

## Slide 6
Top Emerging Risks & Blockers
Risk Description | Urgency | Affected Projects
High volume of medium‑severity unresolved blockers in Project Plan B could trigger schedule slippage and milestone delays. | HIGH | Project Plan B
Continued decline in weighted score for S2P Project may indicate widening performance gaps. | MEDIUM | S2P Project
Zero budget burn to date suggests delayed execution, risking cash‑flow pressure later in the program. | LOW | Project Plan B, S2P Project

## Slide 7
Notable Wins & Positive Signals
Win / Positive Signal | Associated Projects
Both projects achieve a perfect budget score (CPI 1.0) despite no spend, reflecting excellent cost control. | Project Plan B, S2P Project
Milestone on‑time performance exceeds 88% for each project (88.5% and 93.3%). | Project Plan B, S2P Project

## Slide 8
Strategic Recommendations
• Assign a dedicated blocker‑resolution team to Project Plan B and track weekly reduction of unresolved items.
• Review the budget spend plan to align actual expenditures with schedule milestones and avoid idle funds.
• Implement a corrective action plan for S2P Project to stabilize its weighted score, focusing on risk mitigation and stakeholder engagement.
• Capture sentiment data for Project Plan B (e.g., via comment fields) to enable portfolio‑wide sentiment monitoring.
• Tighten task tracking and introduce short‑term schedule buffers to reduce the overdue‑task percentage across both projects.

## Slide 9
Appendix: Detailed Portfolio Metrics
Project Name | RAG | Overall | Schedule | Budget | Blocker | Sentiment
20260708 144914 Project P | AMBER | 76 | 88 | 100 | 0 | 0
20260708 151623 S2P Proje | AMBER | 73 | 93 | 100 | 0 | 43